## Sheet1
PuMpUp Project Cost Estimate
Prepared by: Ankit Prakash | Date: | 2019-05-24
| Units/Hrs. | Cost/Unit/Hrs. | Subtotals | WBS Level 2 totals | % of totals
WBS Items
1.Sketching |  |  |  | 132200 | 45.65%
1.1 Project Manager | 110 | 220 | 24200
1.2 Team Lead | 80 | 200 | 16000
1.3 UI Designer and UI Developer | 400 | 200 | 80000
1.4 HR and testing | 100 | 120 | 12000
2.Architecture |  |  |  | 39500 | 13.64%
2.1 MVP Developer | 100 | 200 | 20000
2.2 MVP Tools | 5 | 1500 | 7500
2.3 HR and testing | 100 | 120 | 12000
3.Development |  |  |  | 3800 | 1.312%
3.1 MS Office licenses | 5 | 100 | 500
3.2 Windows Operating System | 4 | 100 | 400
3.3 Cloud Database | 20 | 30 | 600
3.4 Project management tools | 10 | 30 | 300
3.5 Server | 5 | 400 | 2000
4.Testing (25% of total project cost) |  |  |  | 60000 | 20.72%
5.Training and support |  |  |  | 29500 | 10.19%
5.1 Trainee cost | 80 | 105 | 8400
5.2 Travel cost | 50 | 100 | 5000
5.3 Project Team members | 230 | 70 | 16100
6. Recruiting |  |  |  | 16600 | 5.732%
5.1 Travel cost | 30 | 300 | 9000
5.2 Lodging | 20 | 100 | 2000
5.3 Equipments | 80 | 70 | 5600
6.Reserves |  |  |  | 8000 | 2.762%
Total Project Cost Estimates |  |  |  | 289600 | 100%